CLHO/PHD Joint Leadership Team

PH Modernization Timeline

FC = foundational capability

FP = foundational program

| Activity | Date | Additional SMEs | Document Prep |
| --- | --- | --- | --- |
| Planning and Communication Activities |  |  |  |
| Detailed JLT work plan drafted and sent to Muriel | 6/1/2015 |  | Danna (PHD) |
| Draft talking points for LHD staff and local policy makers drafted and sent to JLT | 6/26/2015 |  | (CLHO) |
| JLT Meeting – review detailed work plan and talking points | 6/18/2015 | N/A | (CLHO) |
| Revised work plan sent to Muriel and Morgan for review | 6/23/2015 |  | Danna (PHD) |
| GovSpace information and updated work plan sent to JLT | 6/24/2015 |  | Danna (PHD) |
| CLHO Meeting – Share progress to date on FCs reviewed so far by JLT | 7/16/2015 |  | (CLHO) |
| CLHO Retreat – Definitions shared with CLHO Members | 9/2015 |  | (CLHO) |
| Policy and Planning |  |  |  |
| FC draft planning doc posted on GovSpace | 6/23/2015 |  | Sara/Tom (PHD) |
| FC draft planning doc open for CLHO review | 6/23-7/8/2015 |  |  |
| PHD Strategic Leadership Council review of Policy & Planning | 6/29/2015 |  | Danna/Sara (PHD) |
| PHD incorporates changes recommended by Strategic Leadership Council | 6/30-7/13/2015 |  | Michael/Sara (PHD) |
| JLT Review webinar | 7/2/2015 8:30-10:30 |  | Michael/Sara (PHD) |
| PHD incorporates changes recommended by JLT | 7/9-7/13/2015 |  | Michael/Sara (PHD) |
| Final review during JLT webinar | 7/16/2015 8:30-10:30 |  | Michael/Sara (PHD) |
| FC definition complete | 7/17/2015 |  | Michael (PHD) |
| Health Equity & Cultural Responsiveness and Community Partnership Development |  |  |  |
| PHD Strategic Leadership Council review of Community Partnership Development | 6/29/2015 |  | Danna/Matt (PHD) |
| PHD incorporates changes recommended by Strategic Leadership Council for Community Partnership Development | 6/30-7/2/2015 |  | Michael/Matt (PHD) |
| FC draft planning docs posted on GovSpace | 7/6/2015 |  | Sara/Tom (PHD) |
| FC draft planning docs open for CLHO review | 7/6-7/17/2015 |  |  |
| JLT Review webinar | 7/16/2015 8:30-10:30 |  | Michael/Matt/Loehn (PHD) |
| PHD incorporates changes recommended by JLT | 7/20-7/24/2015 |  | Michael (PHD) |
| PHD Strategic Leadership Council review of Health Equity & Cultural Responsiveness | 7/27/2015 |  | Danna/Loehn (PHD) |
| PHD incorporates changes recommended by Strategic Leadership Council for Health Equity and Cultural Responsiveness | 7/28-7/29/15 |  | Michael/Loehn (PHD) |
| Final review during JLT webinar | 7/30/2015 8:30-10:30 |  | Michael/Loehn/Matt (PHD) |
| FC definitions complete | 7/31/2015 |  | Michael (PHD) |
| Communications and Assessment & Epidemiology |  |  |  |
| PHD Strategic Leadership Council review of Communications and Assessment & Epidemiology | 6/29/2015 |  | Danna/Cara/Sara (PHD) |
| PHD incorporates changes recommended by Strategic Leadership Council | 6/30-7/17/2015 |  | Michael/Cara/Sara (PHD) |
| FC draft planning docs posted on GovSpace | 7/20/2015 |  | Sara/Tom (PHD) |
| FC draft planning docs open for CLHO review | 7/20-7/31/15 |  |  |
| JLT Review webinar | 7/30/2015 8:30-10:30 |  | Michael/Cara/Isabelle |
| PHD incorporates changes recommended by JLT | 8/3-8/7/2015 |  | Michael/Cara/Isabelle (PHD) |
| Final review during JLT webinar | 8/13/2015 8:30-10:30 |  | Michael/Cara/Isabelle (PHD) |
| FC definitions complete | 8/14/2015 |  | Michael (PHD) |
| Leadership & Organizational Competencies and Emergency Preparedness & Response |  |  |  |
| PHD Strategic Leadership Council review of Leadership & Organizational Skills and Emergency Preparedness & Response | 7/27/2015 |  | Danna/Marti/Vicki (PHD) |
| PHD incorporates changes recommended by Strategic Leadership Council | 7/28-7/31/2015 |  | Michael/Marti/Vicki PHD) |
| FC draft planning docs posted on GovSpace | 8/3/2015 |  | Sara/Tom (PHD) |
| FC draft planning docs open for CLHO review | 8/3-8/14/2015 |  |  |
| JLT Review webinar | 8/13/2015 8:30-10:30 |  | Michael/Marti/Vicki (PHD) |
| PHD incorporates changes recommended by JLT | 8/17-8/21/15 |  | Michael/Marti/Vicki (PHD) |
| Final review during JLT webinar | 8/27/2015 8:30-10:30 |  | Michael/Marti/Vicki (PHD) |
| FC definitions complete | 8/28/2015 |  | Michael (PHD) |
| Prevention & Health Promotion and Environmental Public Health |  |  |  |
| FP draft planning docs posted on GovSpace | 8/17/2015 |  | Sara/Matt (PHD) |
| FP draft planning docs open for CLHO review | 8/17-8/28/2015 |  |  |
| PLACEHOLDER: half day meeting to review each FP planning doc. Participation to be determined by JLT & PHD | Both meetings between 8/17-21 |  | CLHO and Danna/Michael (PHD) |
| PHD Strategic Leadership Council review of Prevention & Health Promotion and Environmental Public Health | 8/25/2015 |  | Danna/Sara/Joey (PHD) |
| PHD incorporates changes recommended by Strategic Leadership Council | 8/26-9/4/2015 |  | Michael/Sara/Joey (PHD) |
| JLT Review webinar | 8/27/2015 8:30-10:30 |  | Michael/Sara/Joey (PHD) |
| PHD incorporates changes recommended by JLT | 8/31-9/4/2015 |  | Michael/Sara/Joey (PHD) |
| Final review during JLT webinar | 9/10/2015 8:30-10:30 |  | Michael/Sara/Joey (PHD) |
| FP definitions complete | 9/11/2015 |  | Michael (PHD) |
| Communicable Disease and Access to Clinical Preventive Services |  |  |  |
| PHD Strategic Leadership Council review of Communicable Disease and Access to Clinical Preventive Services | 8/25/2015 |  | Danna/Cara/Isabelle (PHD) |
| PHD incorporates changes recommended by Strategic Leadership Council | 8/26-8/28/2015 |  | Michael/Cara/Isabelle (PHD) |
| FP draft planning docs posted on Gov Space | 8/31/2015 |  | Sara/Matt (CLHO) |
| PLACEHOLDER: half day meetings to review each FP planning doc. Participation to be determined by JLT & PHD | Both meetings between 8/31-9/4 |  | CLHO and Danna/Michael (PHD) |
| FP draft planning docs open for CLHO review | 8/31-9/11/2015 |  |  |
| JLT Review webinar | 9/10/2015 8:30-10:30 |  | Michael/Cara/Isabelle (PHD) |
| PHD incorporates changes incorporated by JLT | 9/14-9/18/2015 |  | Michael/Cara/Isabelle (PHD) |
| Final review during JLT webinar | 9/24/2015 8:30-10:30 |  | Michael/Cara/Isabelle (PHD) |
| FP definitions complete | 9/25/2015 |  | Michael (PHD) |