| Project Management Outcomes: PH Modernization Grant and communication and outreach work is successfully managed and completed. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | Goal |  |  | Activity | Responsibility |  | Status |
| 8-31-15 | PH Modernization workplan and budget are developed |  |  | Work plan and Budget developed | Morgan |  |  |
|  |  |  |  | Work plan and budget shared with CLHO | Morgan |  |  |
| 7/15-10/15 | PH Modernization Grant is managed and executed by CLHO Staff |  |  | Deliverables of the grant are met | Morgan |  |  |
| 9/15 | Contractor Hired to manage assessment and communication deliverables |  |  | Scope of work developed | Morgan |  |  |
|  |  |  |  | Recruitment conducted & Contractor Hired | Morgan |  |  |
| 10/15-6/16 | Oversee contractor |  |  | Meet regularly with Contractor | Morgan |  |  |
|  |  |  |  | Onboard Contractor | Morgan |  |  |
| Communication Outcome: LPHA leadership and staff are well information of the implications of HB 3100 and understand how to provide input during the planning process. |  |  |  |  |  |  |  |
| Date |  | Goal | Activity |  | Responsibility | Status |  |
| 9-30-2015 |  | Information and communication on HB 3100 is provided to LPHA administrators | Webpage is created on CLHO website. |  | Kathleen | Set up – updating ongoing |  |
|  |  |  | Modernization planning documents are posted on webpage |  | Kathleen | Ongoing |  |
|  |  |  | Outreach to 10 administrators (who don’t regularly attend monthly mtgs.) |  | Kathleen/ Morgan | Complete & Ongoing |  |
| 8-31-2015 |  | Five presentations on public health modernization are provided | General presentations to CLHO, CLHO Caucuses and CLHO Committees on input process: Committees: CLHO CD* CLHO Emergency Prep * CLHO IM * CLHO Healthy Structure * *CLHO HC * Caucuses: CLHO HO, CLEHS, PHAO |  | Kathleen/Morgan | 5 Completed. |  |
| 8-31-2015 |  | Three webinars are conducted on opportunities to engage in modernization process | Three webinars were given the week of July 6-10 on the HB 3100 planning process for HB 3100 Implementation |  | Morgan | 3 Completed |  |
| 9-28-2015 |  | Information and communication on HB 3100 is provided to BOC across the state | Attend 5 AOC District Meetings and present on PH Modernization |  | Morgan/Kathleen |  |  |
| 10-1-15 |  | Communication Materials and Tools are developed for LPHAs to use with local partners, Boards of Health | Contractor hired to develop communications messages/ tools |  | Morgan |  |  |
| Outreach and Engagement Goal: Foundational capabilities and program planning documents are reviewed and feedback is provided. |  |  |  |  |  |  |  |
| Due Date | Goal |  |  | Activity | Responsibility |  | Status |  |
| 9-25-15 | CLHO input included in Foundational Program and Capability documents |  |  | Create PowerPoint for seven webinars | Kathleen |  |  |  |
|  |  |  |  | Facilitate seven webinars | Kathleen/Morgan |  |  |  |
|  |  |  |  | Take Notes and Summarize | Kathleen/Morgan |  |  |  |
|  |  |  |  | Facilitated CLHO retreat to get feedback and work on Foundational Programs and Capabilities | Kathleen/Morgan |  |  |  |
| 9-25-15 | CLHO caucuses, committees, members, and LHDs engaged in planning process |  |  | Solicit feedback at CLHO committees (HST, HS, Healthy Families, Information Management) | Kathleen |  |  |  |
|  |  |  |  | Solicit feedback at CLHO committees (Healthy Communities, CD, Preparedness) | Morgan |  |  |  |
|  |  |  |  | Present at CLHO Caucuses | Morgan |  |  |  |
| Assessment Development Outcome: Development assessment that addresses cross-jurisdictional sharing, health outcomes and health needs, and community involvement |  |  |  |  |  |  |  |
| Date |  | Goal | Activities |  | Responsibility |  | Status |
| 11-30-2015 |  | Solicit feedback from local public health officials and commissioners on assessment process | Present at an AOC meeting |  | Morgan |  |  |
|  |  |  | Present and brainstorm at CLHO Retreat |  | Kathleen/Morgan |  |  |
| 12-31-2015 |  | Finalized modernization of public health assessment |  |  |  |  |  |
| Assessment Implementation Outcome: Implement assessment that address cross-jurisdictional sharing, health outcomes and health needs, and community involvement to determine the function capacity of our public health system |  |  |  |  |  |  |  |
| Date |  | Goal | Activities |  | Responsibility |  | Status |
| 12-2015 |  | Collaborate with PHD on survey implementation | Meet with PHD to determine assessment logistics |  | Contractor |  |  |
| 1-2016 to 2-2016 |  | Engage LHDs on how to assess foundational capabilities and programs | Visit with 20 LHDs to prepare for assessment |  | Contractor |  |  |
|  |  |  | Facilitate 3 regional meetings to discuss CJS |  | Contractor |  |  |
| 6-2016 |  | 34 LHDs complete modernization of public health assessment | Call LHDs to follow-up on assessment progress |  | Contractor |  |  |