Program Element #05:  Health Impact Assessment (HIA) Program (Phase I): Building Capacity in Local Public Health Authorities

- Description.  Funds provided under the Financial Assistance Agreement for this Program Element may only be used, in accordance with and subject to the requirements and limitations set forth below, to build capacity to perform Health Impact Assessments (HIA), and evaluation within LPHA’s service area.

- Local Activities in Support of Building HIA capacity. To comply with performance standards of this program, LPHA must engage in activities as described in subsections 2.a. through 2.e. below. The purpose of these activities is to support the development of an HIA intended to make the finished project more supportive of the health of local citizens by incorporating health into the decision making process on a project in LPHA’s service area.  NOTE:  LPHA must complete the planned activities in its Local Program Plan before August 28, 2015 to retain eligibility to receive funding under this Program Element if future funding is made available.

- Conducting an HIA on a policy or built environment project within the jurisdiction of the LPHA.  HIA is a tool designed to incorporate health into decision-making processes when it is not normally considered. In order to make the work of HIA successful it is important that an appropriate project or policy be chosen as the subject and that stakeholders are engaged in the process and understand the utility of HIA. LPHA is expected to use the best practices steps of Screening, Scoping, Assessment, Recommendations and Reporting, and Monitoring and Evaluation steps of HIA in their project. A full explanation of the steps can be found at: http://www.humanimpact.org/Tools.html. The goal of this Program Element is to complete one HIA or built environment project by August 3, 2014 and build the capacity within LPHA to conduct future HIA on projects or policies within their community.

- Collaborating with Partners. Convene and facilitate partnerships with community organizations, planning commissions, and others representing various groups who have a stake in the project that the LPHA chose for an HIA or built environment project. As much as possible, this group should include those that have influence over the final project or who have the ability to help get the recommendations of the HIA considered in the planning process.

- Disseminating the results of the HIA to partners and groups that have a stake in the project on which the HIA was done.  The results of the HIA should be disseminated to stakeholders in a format that is appropriate to the project.  Examples of appropriate formats include but are not limited to: formal written report; a letter to the decision making body; a fact sheet; or presentation to the decision makers.  The results of the HIA should also be posted to the website of the LPHA and made widely available.

- Presenting the process of HIA and the results of the project: The results of the HIA should be shared with other public health professionals at the local, regional or national level by December 31, 2015.  The presentation should introduce the concept of HIA as well as include a case study of the LPHA’s project. The goal of the presentation is to raise awareness of HIA and the utility of the process.

- Preparing a final written report to OHA in the project: LPHA will provide a written final report to OHA that includes a project description, activities conducted, and outcomes. This written report should contain lessons learned, best practices, identified challenges and success stories within the context of the LPHA implementation of the HIA steps. It should also outline contacts and collaborations, issues/concerns with recommendations for improvements to OHA’s grant. The final written report is due August 28, 2015.

- Procedural and Operational Requirements.  By accepting and using the financial assistance funding provided OHA under the Financial Assistance Agreement and this Program Element, LPHA agrees to conduct HIA activities in accordance with the following requirements:

- LPHA will conduct all HIA as described in this Program Element.

- LPHA will assure that its local program is staffed at the appropriate level to address subsections 2.a. through 2.e. of this Program Element. Funds for this program element must be directed to personnel and other expenses in support of subsections 2.a. through 2.e.

- LPHA will provide documentation of activities and outcomes upon the completion of each HIA step as outlined in Section 2a.

- LPHA will participate in monthly calls (approximately five, 45 minute calls) and online trainings that meet LPHA needs as they conduct their assessment.

- Reporting Requirements.  LPHA must submit the result of the HIA or built environment project to OHA and post the information on the LPHA’s website by September 15, 2015. LPHA is not required to complete the Public Health Revenue and Expenditure form located in Exhibit E of the Agreement for activity funding pursuant to this Program Element.