November 12, 2015

Public Health Modernization Manual: Detailed Timeline

| Activity | Start Date | Complete Date | Who |
| --- | --- | --- | --- |
| JLT webinar to review modernization manual | 11/12/15 8:30-10:30 am |  | JLT |
| Incorporate JLT edits to modernization manual | 11/12/15 | 11/13/15 | Technical writer and PHD modernization staff |
| Open modernization manual for public comment | 11/16/15 | 12/1/15 | PHD modernization staff |
| Public meeting #1 to review modernization manual | 11/18/15 3-4 pm |  | PHD modernization staff Interested parties |
| Public meeting #2 to review modernization manual | 11/20/15 11 am-12 pm |  | PHD modernization staff Interested parties |
| Compile public comment | 12/1/15 | 12/2/15 | PHD modernization staff |
| JLT webinar to review/incorporate public comment | 12/3/15 8:30-10:30 am |  | JLT |
| Incorporate final comments, consider draft final for current period, share with assessment contractor | 12/3/15 | 12/4/15 | PHD modernization staff |
| Use modernization manual to create assessment tool | 12/4/15 | 1/4/16 | Assessment contractor |
| Review and make final edits to the modernization manual following the assessment period | 2/15/16* | 3/15/16* | JLT |
| Promulgate rules for HB 3100; adopt modernization manual by reference | 4/15/16* | 5/31/16* | PHAB PHD modernization staff |

*Estimated dates, may change based on the course of work.

For more information, visit healthoregon.org/modernization or contact publichealth.policy@state.or.us.