**Survey**

**Nov/Dec 2015**

**Evidence-informed strategy research**

**Aug/Sept 2015**

**MCH Title V Grantee Meeting**

**February 9, 2016**

**Topic-specific webinars**

**Oct 26-Nov 5**

**Development and Launch of Strategies and Measures for Oregon’s 2016- 2020 MCH Title V Priorities**

Discussion of potential strategies for each priority with a broad range of MCAH partners.

Strategies refined/ potential measures added

Topics include:

* Title V MCH program changes;
* Planning, implementation, measurement, and reporting guidance;
* Menu of strategies for each priority;
* Ongoing support, networking and Technical assistance needs

Title V LHA and Tribal grantee survey on draft strategies for all priorities.

Compilation of potential strategies from Oregon and national sources for each of Oregon’s Title V national priorities

**MCH Title V plan guidance disseminated**

**February 15, 2016**

**Implementation parameters finalized Jan 1015**

**Local Title V implementation parameters/guidelines**

**drafted - Nov/Dec 2015**

**Menu of strategies/ESMs finalized**

**Mid- February**

**Grantee MCH Title V plans due**

**April 1st, 2016**

**Implementation preparation**

**April- June 2016**

**July 15, 2016**

MCH Title V Block Grant submitted to HRSA

**Strategies and measures launched**

**July 2016**

Application includes:

* State performance measures
* Evidence-based/informed strategic measures for each of the 8 selected National priorities
* Implementation action plan

LHAs and tribes indicate in annual plans which priorities, strategies/ measures they will implement with Title V funds

State and local activities including staff development, refinement of data collection and tracking systems, etc.

State and Local Title V work and data collection on selected strategies begins

State Title V staff review plans

LHAs/Tribes select priorities, strategies/measures

Title V leadership finalizes and disseminates menu of strategies, local implementation guidance and MCH Title V Plan template

**State-specific priority strategy development**

**State Performance Measures finalized – April/May 2016**

**State Performance Measure Development – Feb- March 2016**