Triennial Review Improvement

Project Charter

| Point of Contact (for Implementation and Evaluation): | Jan Kaplan Morgan Cowling | Facilitator(s) (for facilitation and support): | Matt Gilman Kristen Lacijan |
| --- | --- | --- | --- |
|  | ## Name, Office/Unit |  |  |
| Participants: | - Erin Mowlds, Washington County Department of Health and Human Services - Kathleen Johnson, Conference of Local Health Officials - Pam Hutchinson, Marion County Public Health Department - Karen Woods, Wheeler County Health Department - Claire Smith, Multnomah County Health Department - Danna Drum, Office of the State Public Health Director (OSPHD) - Susan Greathouse, Women, Infants, and Children (WIC) - Jan Kaplan, OSPHD - Carole Yann, OSPHD - Ronit Zusman, OSPHD |  |  |
| Sponsors: | - Priscilla Lewis, Deputy Director, Oregon Public Health Division - Morgan Cowling, Executive Director, Conference of Local Health Officials (CLHO) |  |  |
| AIM/Problem Statement: | - Improve the current triennial review process in an effort to reduce redundant and duplicative requirements while maintaining required contract compliance. |  |  |
| Primary goal of event: | - Reduce redundant and duplicative requirements and improve the triennial review process while maintaining contract compliance. - Restructure the review process in a way that could free both State and Local staff time for other programmatic activities. - Allow for a standards review process that aligns with accreditation work and the future of public health conceptual framework. |  |  |
| Scope: | - TBD |  |  |
| Customers/Clients: | - Local health departments, Public Health Division programs, funders, legislators |  |  |
| Key Dependencies: | - Impact of current and/or future public health emergencies |  |  |
| Constraints: | - Rules, statutes, state and federal grant requirements |  |  |
| # Expected Benefits: | Quality Impact Goal: Service Impact Goal: - Reduce the amount of time required to prepare documentation for the triennial review. - Decrease the amount of duplicative paperwork required for the triennial review. People Impact Goal: - Increase the number of local public health department staff members who view the triennial review process as a valuable process. |  |  |
| Key Performance Indicators/Metrics: | Cycle time; Current: ?; Goal: TBD. Error rate; Current: ?; Goal: TBD. Staff Satisfaction; Current: ?; Goal: TBD. |
| Timing and Logistics: | Event; Date/Time; Location. TBD; TBD; TBD. |