Triennial Review Improvement

Project Charter

| Point of Contact (for Implementation and Evaluation): | Jan Kaplan Morgan Cowling | Facilitator(s) (for facilitation and support): | Matt Gilman Kristen Lacijan |
| --- | --- | --- | --- |
|  | ## Name, Office/Unit |  |  |
| Participants: | - Kathleen Johnson, Conference of Local Health Officials (CLHO) - Pam Hutchinson, Marion County Public Health Department - Claire Smith, Multnomah County Health Department - Erin Mowlds, Washington County Department of Health and Human Services - Danna Drum, Office of the State Public Health Director (OSPHD) - Susan Greathouse, Women, Infants, and Children (WIC) - Jan Kaplan, OSPHD - Carole Yann, OSPHD - Ronit Zusman, OSPHD |  |  |
| Sponsors: | - Priscilla Lewis, Deputy Director, Oregon Public Health Division - Morgan Cowling, Executive Director, CLHO |  |  |
| AIM/Problem Statement: | - By June 2015, this committee will clarify the purpose, goals, frequency and length of a review that increases efficiencies and reduces duplication of internal and external requirements present in the current review process. |  |  |
| Primary goal of event: | - Reduce redundant and duplicative requirements and improve the triennial review process while maintaining contract compliance. - Restructure the review process in a way that could free both State and Local staff time for other programmatic activities. - Allow for a standards review process that aligns with accreditation work and the future of public health conceptual framework. |  |  |
| Scope: | - A revised review process will be piloted by three counties (small, medium, and large) by December 2015. The revised process will result in reduced state staff time (travel and preparation) and increased local health department satisfaction. |  |  |
| Customers/Clients: | - Local health departments, Public Health Division programs, funders, legislators |  |  |
| Key Dependencies: | - Impact of current and/or future public health emergencies |  |  |
| Constraints: | - Rules, statutes, state and federal grant requirements |  |  |
| # Expected Benefits: | Quality Impact Goal: Service Impact Goal: - Reduce the amount of time required to prepare documentation for the triennial review. - Decrease the amount of duplicative paperwork required for the triennial review. People Impact Goal: - Increase the number of local public health department staff members who view the triennial review process as a valuable process. |  |  |
| Key Performance Indicators/Metrics: | Cycle time; Current: ?; Goal: TBD. Error rate; Current: ?; Goal: TBD. Staff Satisfaction; Current: ?; Goal: TBD. |