# Technical Assistance Plan for the Coalition of Local Health Officials AIMHI Project

DRAFT

## Technical Assistance Goals:

- Provide on-going technical assistance based on needs identified in regional meetings.

- Provide on-going technical assistance to state and local health departments to make progress in implementation using the roadmap and tools developed.

- Assist communities in the identification of additional partnerships in areas ripe for increased sharing (i.e. state and local, CJS, community partner sharing) or regional models.

- Capture feedback from the PHD, local health departments, and county commissioners to ensure the developed tools support implementation processes.

## Technical Assistance Objectives:

- Conduct proactive individual or small group technical assistance encounters with each community & state HD

- Track all TA encounters and capture information about successes and challenges

- Prepare and conduct 4 webinars for state and local health departments

## Proposed Schedule:

Four Webinars:

November— Managing Change: Three Simple Things to do Today or Talking to Your Community about Public Health and Public Health Modernization || Rede and LHD co-presenter || (Supported by Rede; Proposed for the last week of November)

December— Preview the AIMHI Roadmap || Caitlin (supported by Rede)

January— Communications in Partnership with McCabe Messaging + Roadmap booster session

February— Review of Equity Tools + Roadmap booster session

For all webinars, Rede will contact and engage presenters; develop presentations, under the direction of presenters; distribute invitations; host, staff, and record webinars. Webinars can be moderated by CLHO staff

## Proactive TA Meetings:

December— 11 meetings (State + LHDs TBD)

January—12 meetings (LHDs TBD)

February— 12 meetings (LHDs TBD)

## Responsive TA:

- Respond to requests from CLHO staff and CLHO members within one business day

- Ascertain needs

- Conduct research, if necessary

- Respond

- Documents TA

## Final TA Report with Recommendations:

Submitted at the conclusion of the project