TO:  CLHO Board & CLHO Committee Chairs and Members

FR:  Morgan Cowling, CLHO Executive Director

RE:  Committee Transition Timeline & Plan for Review

_________________________________________

October 19th Meeting

- Adopt Committee Transition Timeline & Plan

- Ask CLHO Healthy Structure to come up with a couple of important “best practices” for CLHO Committees to try and adopt including:

  - Charter/ Workplan Template (template updated from 2013 committee transition) that includes annual review of PE, Funding formula and performance measures

  - Communications guidance (updated from 2001 committee guidance)

- Begin recruitment for new committees

November

- CLHO Chair and Executive Director work with state partners to identify the right people to participate in the new committees & Support Structures for Committees

- Identify transition training/ orientation plan

December 21st Meeting -

- Appoint new slates of State & Local Committee Members

- Approve CLHO Committee Charter Template

- Review & Adopt Communications Plan for Committees

January 1, 2018 - Launch date for new CLHO Committees

January / February -

- new committees begin reviewing and adopting Committee Charters