| Objective #1: Taking an active role in the development of public health legislation, ordinances and policies at local and state levels and, when appropriate, at federal levels. [Policy & Advocacy] Objective #2: Promoting public funding to effectively implement and sustain local public health services and programs to ensure all Oregonians have access to public health protections. [Funding Advocacy] |  |  |
| --- | --- | --- |
| Strategy A: Develop and pass three priority issues for the 2021 legislative session. |  |  |
| Activities | Responsible | Timeline |
| - Identify potential public health issues that need to be addressed - Collect state and local data to support priority of the issue & update white papers - Approve priority issues for ’21 legislative session - Develop coalition partners to support public health issues including County GR, AOC, Statewide organizations interested in public health - Meet with legislators prior to the ’21 session - Continue to work with legislators on support of priority issues during ’21 legislative session | Leg Committee CLHO Staff CLHO Board CLHO Staff CLHO Staff CLHO STaff | Jan ‘20 Jan ‘20 August ‘20 Summer ‘20 Fall ‘20 Jan – June ‘21 |
| Strategy B: Identify and support collaborations between local public health and CCO 2.0 and Early Learning hubs |  |  |
| Activities | Responsible | Timeline |
| - Develop strategies and opportunities for local public health to engage with CCOs and Early Learning hubs - Track CCO 2.0 and Early Learning Council strategic plan - Identify strategies for CCO 2.0 discussion and next steps - Update reference guide for CCO 2.0 engagement and website | PH Admins Sierra Sierra Sierra | Sept ‘19 Sept ‘19 – ‘21 On-going Dec ‘19 |
| Strategy C: Update and refine policy statements to support legislative education and advocacy |  |  |
| Activities | Responsible | Timeline |
| - Review current policy statements - Identify and develop missing and needed policy statements - Research and draft new policy statements - Continue to develop and refine policy statements and develop new policy statements - Review and approve edited and new policy statements | Leg Comm Leg Comm CLHO Staff CLHO Board CLHO Board | Oct ‘19 Nov ‘19 Dec ‘19 Feb/ March ‘20 June ‘20 |
| Strategy D: Train, support and prepare local public health officials for education and advocacy during the ’21 legislative session. |  |  |
| Activities | Responsible | Timeline |
| - Develop an overview guide education vs advocacy and state rules for public officials - Identifying additional local needs for advocacy support - Provide 101 advocacy guide for local public health (webinar) - Provide 202 advocacy training for local public health (webinar) - Provide 1:1 training and support for legislator engagement - On-going legislative updates | CLHO Staff Leg Comm CLHO Staff CLHO Staff CLHO Staff CLHO Staff | July ‘20 June/July ‘20 August ‘20 Dec ‘20 Jan - June ‘21 Jan- June ‘21 |

| Objective #3: Supporting excellence in public health knowledge and skills in the local public health workforce. [Workforce] |  |  |
| --- | --- | --- |
| Strategy A: Build and run a Leadership Development Program that builds knowledge and supports public health administrators, supervisors and managers. |  |  |
| Activities | Responsible | Timeline |
| - Support a core group of PH Administrators to participate in the Leadership Development Program - 6 webinars/ 6 core group meetings - Create mentorship-like connections - Develop a new administrator onboarding protocol | CLHO Staff Sierra | On-going Dec ‘19 |
| Strategy B: Support current workforce through caucuses / region meetings |  |  |
| Activities | Responsible | Timeline |
| - Develop proposal for a supervisor/manager caucus | CLHO Staff | Dec ‘20 |
| Strategy C: Engage with Higher Education to promote the needs of the public health workforce |  |  |
| Activities | Responsible | Timeline |
| - Meet with OSU and OHSU-PSU Schools of Public Health - Identify areas for engagement | Sierra Sierra | Oct ‘19 Ongoing |
| Strategy D – Develop a local public health agreed upon definition of health equity and apply it in the daily work of the Coalition (and potentially the Conference) |  |  |
| Activities | Responsible | Timeline |
| - CLHO Board approve next steps for health equity work - bring people together, build definition and develop skills for application - Identify consultant to work with Local Public Health Officials to develop a plan to move forward a working definition of health equity - Bring together local public health officials to develop an agreed upon working definition of health equity and develop tools for application - Begin to apply the working definition within Conference of Local Public Health Committees and internal CLHO structure | CLHO Staff CLHO Staff PH Admins CLHO Board / Systems & Innovation | Oct/ Nov ‘19 Jan ‘20 June ‘20 Sept – Dec ‘20 |
| Strategy E - Visits to local public health administrators to support advocacy and workforce objectives |  |  |
| Activities | Responsible | Timeline |
| - CLHO Staff make five visits to local public health departments - CLHO Staff make five visits to local public health departments | CLHO Staff CLHO Staff | Oct/ Nov ‘19 Spring ‘20 |

| Objective #4: Communicating the value and critical role of local public health to commissioners, community partners and legislators. [Partner engagement in support of Objectives #1-3] |  |  |
| --- | --- | --- |
| Strategy A: Actively participate in statewide coalitions on behalf of local public health officials |  |  |
| Activities | Responsible | Timeline |
| - Participate on the Oregon Partners for Tobacco Prevention statewide tobacco coalition - Participate on the Health Kids Learn Better statewide healthy kids coalition - Participate on the Allies for a Healthier Oregon statewide health coalition - Identify additional statewide coalitions that local public health should be represented at | Morgan Sierra Morgan CLHO Staff | Forever Forever Forever On-going |
| Strategy B: Engage with Commissioners and AOC |  |  |
| Activities | Responsible | Timeline |
| - Regularly attend the monthly AOC Health & Human Services Steering Committee meetings - Meet with Commissioners in-district with local health administrators | Morgan & ____ CLHO Staff | On-going On-going |

| Objective #5: Communicating the value and critical role of local public health to commissioners, community partners and legislators. [Communications tools in support of Objectives #1-3] |  |  |
| --- | --- | --- |
| Strategy A: Continue to market and communicate the value of public health modernization |  |  |
| Activities | Responsible | Timeline |
| - Distribute monthly newsletter that features local public health work - Engage legislative readership by notifying legislators when a county in their district is featured in the newsletter | Sierra Sierra | Ongoing Ongoing |
| Strategy B: Promote legislative priorities |  |  |
| Activities | Responsible | Timeline |
| - Develop one-pagers in for 2020 priorities - Develop one-pagers in support of legislative proposals | CLHO Staff CLHO Staff | Dec ‘20 - Jan ‘20 Aug-Sep ‘20 |
| Strategy C: Maintain the CLHO Website |  |  |
| Activities | Responsible | Timeline |
| - Assess website utility and needed updates | CLHO Staff | Mar ‘20 |

| Objective #6: Support and develop CLHO staff |  |  |
| --- | --- | --- |
| Strategy A: Support continuing education opportunities for CLHO staff |  |  |
| Activities | Responsible | Timeline |
| - Identify training and potential leadership development opportunities for CLHO staff to develop skills in support of the CLHO mission - Identify additional budget request to support leadership development opportunities for CLHO staff | CLHO Staff CLHO Treasurer & CLHO STaff | Oct/ Nov ‘19 March ‘20 |