Timeline and plan for new Program Manager

May 16 – CLHO Board discussion of the timeline and transition plan

- Recruit a “hiring committee” to review the job description and participate in the hiring process and interviews

May 16 – May 30th – Hiring Committee

- Review and update job description

- Hold and set interview dates

June 1, 2019 – Post Job Description & Supplemental Question(s)

Macslist.org

OHSU/ PSU – School of Public Health job page

OSU List –serve

CLHO Facebook page

June 15, 2019 – Applications Dues

- Morgan paper cut down to 10 candidates

- Committee review and cut from 10 down to 5

- Morgan schedule 5 interviews

- Morgan dust off interview questions

June 24 – 28th, 2019 - Interviews

July 1, 2019 – Offer Made/ Negotiations

July 22nd, 2019  - Goal Start Date to overlap w/ Caitlin for one week