## Workplan Template Instructions
GRANT CYCLE
July 1, 2020 – June 30, 2021
GENERAL STRATEGIES TO DEVELOP YOUR WORKPLAN
Refer to Section 4.f of this Program Element for more information.
WORKPLAN GOALS
CDC Capability: Identify which CDC PHEPR Capability your program goals will address.
PROGRAM GOALS: Establish at least three broad program goals that address gaps, operationalize plans, and guide workplan activities. Goals are big picture outcomes you want to achieve from your workplan activities and must support a CDC PHEPR Capability.
WORKPLAN COLUMNS
GOAL #: Identify which goal this objective will accomplish.
OBJECTIVES: Use clear and measurable objectives with identified time frames to describe what the LPHA will complete during the grant year. Objectives support goals. They are what you plan to accomplish.
PLANNED ACTIVITES: Activities are how you plan to accomplish your goals.
TARGET DATE: The date you plan to complete or conduct the activity.
DATE COMPLETED: When updating the workplan, record date of the completed activities and/or objective.
ACTUAL OUTCOMES: To be filled in after activity is conducted. Describe what is achieved and the products created from this activity.
NOTES: Additional explanation such as AAR/IP references. If activity not completed, please indicate reason in this column.
WORKPLAN CATEGORIES
ESF-8 PARTNER COLLABORATION: List all meetings regularly attended or led by PHEPR staff and any special collaborations you will be conducting this year. Reference 4c of the PE-12 for a more detailed description of partner collaborations.
PHEPR PLANNING: List all plans, procedures, updates, and revisions to be conducted in accordance with your planning cycle or any other scheduled planning activities You should also review all After Action Reports/Improvement Plans completed during the previous grant year to identify planning activities that should be conducted this year.
COMMUNITY OUTREACH AND PUBLIC INFORMATION: List activities you plan to conduct that enhance community preparedness or resiliency including community events, public presentations, and media campaigns not associated with response activities.
STAFF PHEPR TRAINING: List planned preparedness trainings, workshops attended by staff.
PHEPR DRILLS and EXERCISES: List drills and exercises you plan to conduct or significantly participate in and identify annual exercises in accordance with your approved MYTEP and as required in Section 4.j. of this Program Element. This section of the workplan may qualify as your MYTEP, or you may use a format that best meets your LPHA’s needs.
ESF-8 INCIDENTS AND RESPONSE ACTIVITIES: List incidents and response activities that occurred during the current grant cycle. If an OERS Number was assigned, please include the number. Identify the outcomes from the incident and response activities, include date(s) of the incident and action taken.
UNPLANNED ACTIVITY: List activities or events that were not included when workplan was first approved. Please identify outcomes for the unplanned activity, include date(s) of occurrence and actions taken.

## Due Dates
Important PHEP Dates for LPHAs
Program Element 12 (PE-12)
Date | Fiscal Year | Item
2020-06-30 | FY20 | End of fiscal year 2020. Deadline to complete FY20 work plan activities and expend FY20 funds.
2020-07-01 | FY21 | Start of fiscal year 2021
2020-08-15 | FY21 | Proposed budget due for award period July 1, 2020 - June 30, 2020 using actual amounts.
2020-08-15 | FY20 | FY20 year-end reviews must take place between April 1 and August 15 in coordination with HSPR Liaison.
2020-08-15 | FY21 | Proposed budget, work plan, & MYTEP due.
2020-09-15 | FY21 | Final approved budget, work plan, and MYTEP due.
2020-12-01 | FY21 | Public Health Preparedness Capability Surveys completed by LPHAs.
2021-03-31 | FY21 | Mid-year reviews may take place between October 1 and March 31.
2021-06-30 | FY21 | End of fiscal year 2021. Deadline to complete FY21 work plan activities and expend FY21 funds.
2021-08-15 | FY21 | FY21 year-end reviews must take place between April 1 and August 15 in coordination with HSPR Liaison.

## Work Plan Template
xx County
Goal 1:
Goal 2:
Goal 3:
ESF-8 Partner Collaboration
Goal # | Objectives | Planned Activities | Target Date | Date Completed | Progress/Actual Outcomes | Notes
Unplanned Partner Collaborations
PHEPR Planning
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | Date Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
Unplanned Planning Activities
Goal # | Planning Activity Description: (Name of resulting or future plan, participating staff or partners.) |  |  | Date Completed | Additional Notes
PHEPR Community Outreach and Public Information
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | Date Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
Unplanned Community Outreach or Public Information Activities
Activity Description: (Name of community event or incident, type of information shared.) |  |  |  | Date Completed | Additional Notes
Activity Description: (Name of community event or incident, type of information shared.)
Staff PHEPR Training
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | Date Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
Unplanned Training and Education
Goal # | What Objective Did This Unplanned Training or Education Meet? | Name of Training |  | Date Completed | What staff participated? | Additional Notes
PHEPR Drills and Exercises
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | Date Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
Unplanned Drills and Exercises
Goal # | What Objective(s) Did This Unplanned Drill or Exercise Meet? | Name of Drill or Exercise |  | Date Completed | What staff or partners participated? | Additional Notes
ESF-8 INCIDENT AND RESPONSE ACTIVITIES
CDC Cap. #s | Incident Name/OERS # |  | Date(s) | Activities and Outcomes |  | Date AAR Completed

## Work Plan Minimum Req.
xx County
Goal 1: Increase the capacity of LPHA to prevent, protect, mitigate, respond to, and recover from emergencies and threats impacting the health of the jurisdiction.
Goal 2: Strengthen partnerships within jurisdiction, region, and state to build community capacity for public health preparedness and response.
Goal 3: Maintain and strengthen the validity and currency of all LPHA ESF-8 plans.
ADMINISTRATIVE REQUIREMENTS
Activity |  |  | Date Due | þ when Completed | Notes
| Submit Budget Draft for approval |  | August 15, 2020
| Submit Work Plan & MYTEP Draft for approval |  | August 15, 2020
Workplan meets at minimum the minimum PE-12 requirements of the PE-12 contract.
MYTEP demonstrates continuous improvement and progress toward increased capability to perform functions and tasks associated with the CDC Public Health Emergency Preparedness and Response Capabilities.
MYTEP includes priorities that address lessons learned from previous exercises events, or incidents as described in the LPHA’s AAR/IP.
LPHA has worked with Emergency Management, local health care partners and other community partners to integrate exercises and align MYTEPs, as appropriate.
MYTEP includes at least two exercises per year if LPHA’s population is greater than 10,000 and one exercise per year if LPHA’s population is less than 10,000.
MYTEP demonstrates a cycle of exercises that increase in complexity over a three-year period.
| Final Budget Approved by HSPR |  | September 15, 2020
| Local public health leadership will review and approve PHEPR workplans. |  | September 15, 2020
| Final Workplan Approved by HSPR |  | September 15, 2020
| Capabilities Assessment |  | December 1, 2020 |  | Data acquired through this assessment should guide your current work plan at the mid year review and your future work plans at the time of development.
| Mid-year work plan review completed |  | February 15, 2021
| Year-end work plan review completed |  | August 15, 2021
| Triennial Review |  | (add date for your jurisdication) |  | See OHA PHD Triennial Review Schedule: https://www.oregon.gov/oha/PH/PROVIDERPARTNERRESOURCES/LOCALHEALTHDEPARTMENTRESOURCES/Documents/Triennial%20Review%20Tools/Agency-Review-Schedule.pdf
| Conduct a public health jurisdictional risk assessment once every five years, in collaboration with local ESF-8 partners |  | TBD by OHA |  | Data acquired through this assessment should guide your planning efforts and your multi-year training and exercise plans. Timeline for jurisdictional risk assessment to be established by OHA.
ESF8 Partner Collaboration
Goal # | Objectives | Planned Activities | Target Date | þ when Completed | Progress/Actual Outcomes | Notes
1, 2 | LPHA will leverage partnerships with local, regional, and statewide ESF-8 partners hat support public health and medical responses to increase its capacity to provide to ESF-8 services locally. | LPHA will work to develop and maintain a portfolio of community partnerships to support preparedness, mitigation, response and recovery efforts. | ongoing | Mid Year: Year End:
|  | LPHA will participate in local, regional, and statewide emergency preparedness subcommittees, work groups and projects for the sustainment of public health emergency preparedness, as appropriate. | ongoing | Mid Year: Year End:
|  | LPHA will collaborate with HCC partners to develop and maintain plans, conduct training and exercises, and respond to public health threats and emergencies using a whole-community approach to preparedness management. | ongoing | Mid Year: Year End:
|  | LPHA will participate in a minimum of 75% of statewide HSPR-hosted monthly conference calls for LPHAs and Tribes. | ongoing | Mid Year: Year End:
|  | LPHA will participate in a minimum of 75% of statewide HSPR-hosted monthly conference calls for LPHAs and Tribes. | monthly | Mid Year: Year End:
Unplanned Partner Collaborations
PHEPR Planning
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | þ when Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
1-3 | By June 30, LPHA will maintain and bring current its all-hazards plans that provide procedures and guidance to respond to any emergency or threat that may impact the health of the county | ESF-8: LPHA will collaborate with emergency manager on the update of the ESF-8 in the County Emergency Operations Plan in accordance with the local emergency management schedule.
BASE PLAN: LPHA will maintain and update All-Hazards Base Plan as needed when incidents or exercise improvement items necessitate a change, but not less than every 2 years.
COOP: LPHA will maintain and update a Continuity of Operations Plan as needed when incidents or exercise improvement items necessitate a change, but not less than every 2 years.
MCM: LPHA will maintain and update a Medical Countermeasures and Dispensing Plan as needed when incidents or exercise improvement items necessitate a change, but not less than every 2 years.
LPHA will maintain and update a Communications Plan as needed when incidents or exercise improvement items necessitate a change, but not less than every 2 years.
All ESF-8 supporting plans will be maintained and updated not less than every 2 years.
LPHA will update its ICS organizational chart annually at minimum and will maintain this chart within its all hazard base plan to identify LPHA staff that will respond to an emergency annually at minimum.
An index or table of contents that includes supporting plans will be included in the All-Hazard Base Plan that includes a record of change to include, date of last revision, purpose for revision, revision made, and person who made revision.
1-3 | LPHA will increase its capacity to respond to an event requiring medical countermeasures dispensing and distribution. | LPHA will maintain and update a Medical Countermeasures and Dispensing Plan as needed when incidents or exercise improvement items necessitate a change, but not less than every 2 years.
1-3 | LPHA will increase its capacity to serve persons with access and functional needs. | Plan updates include considerations for persons with access and functional needs. | ongoing
Unplanned Planning Activities
Goal # | Planning Activity Description: (Name of resulting or future plan, participating staff or partners.) |  |  | Date Completed | Additional Notes
PHEPR Community Outreach and Public Information
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | þ when Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
1 | LPHA will maintain ability to inform public about any emergency or threat that may impact the health of the jurisdiction. | Maintain local media contact lists. | ongoing | Mid Year: Year End:
|  | Maintain ability to distribute announcements to the public, including through social media. | ongoing | Mid Year: Year End:
|  | Maintain awareness of and access to PHD CERC toolkits | ongoing | Mid Year: Year End: |  | https://www.oregon.gov/oha/ph/preparedness/partners/pages/riskcommunicationtools.aspx
Unplanned Community Outreach or Public Information Activities
Activity Description: (Name of community event or incident, type of information shared.) |  |  |  | Date Completed | Additional Notes
Activity Description: (Name of community event or incident, type of information shared.)
PHEPR Staff Training
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | þ when Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
1, 2 | Preparedness-funded staff will receive ongoing training with statewide partners | Designated staff will attend Oregon Prepared Workshop, as able. | March/April 2021 |  |  | LPHA staff are not required to attend conferences though it is recommended, particularly for PHEP-funded staff as part of ongoing training plan.
|  | Designated staff will attend Oregon Conference of Epidemiologists, as able. (Sunriver.) | April/May 2021
1 | 100% of public health staff will have an understanding of their role in preparedness and response to ensure an adequate response and to maintain NIMS compliance. | A written training plan will be developed in accordance with NIMS principles. |  |  |  | An approved training plan may be detailed in this workplan or may be a stand-alone document.
Training records will be maintained for all PHEPR-related trainings for all staff.
New LPHA staff will be oriented to emergency preparedness as a foundational capability.
100% of LPHA staff will be trained in IS-100 & IS-700.
|  | 100% of PHEP-funded staff will successfully complete IS-100, IS-200, IS-700, & IS-800. |  |  |  | https://training.fema.gov/is/crslist.aspx
|  | Staff designated for incident command roles will take ICS-300 when offered in the area. | When Available
|  | PHEP Training records will be maintained. | Ongoing
Unplanned Training and Education
Goal # | What Objective Did This Unplanned Training or Education Meet? | Name of Training |  | Date Completed | What staff participated? | Additional Notes
PHEPR Drills and Exercises
Goal # | Objectives (BIG PICTURE: What you plan to accomplish.) | Planned Activities (How you plan to accomplish the objective.) | Target Date | þ when Completed | Progress/Actual Outcomes (what you actually accomplished) | Notes (AAR references, carryover explanations, etc.)
| FY21 EXERCISE #1: (Title or brief description, including primary partnerships) | Send Event Notification to PHEP Liaison 30 days in advance of exercise.
Conduct or Participate in Exercise
Complete AAR within 60 days of exercise
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
| FY21 EXERCISE #2: (Title or brief description, including primary partnerships) | Send Event Notification to PHEP Liaison 30 days in advance of exercise.
Conduct or Participate in Exercise
Complete AAR within 60 days of exercise
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
| FY22 EXERCISE #1: (Title or brief description, including primary partnerships) | Send Event Notification to PHEP Liaison 30 days in advance of exercise.
Conduct or Participate in Exercise
Complete AAR within 60 days of exercise
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
1-3 | FY22 EXERCISE #2: Cascadia Rising 2022 | Send Event Notification to PHEP Liaison 30 days in advance of exercise. | May 14, 2022
|  | Conduct or Participate in Exercise | June 13-17, 2022 |  |  | Required participation level TBD.
|  | Complete AAR within 60 days of exercise | August 16, 2022
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
| FY23 EXERCISE #1: (Title or brief description, including primary partnerships) | Send Event Notification to PHEP Liaison 30 days in advance of exercise.
Conduct or Participate in Exercise
Complete AAR within 60 days of exercise
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
| FY23 EXERCISE #2: (Title or brief description, including primary partnerships) | Send Event Notification to PHEP Liaison 30 days in advance of exercise.
Conduct or Participate in Exercise
Complete AAR within 60 days of exercise
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
| FY24 EXERCISE #1: Required Statewide Medical Countermeasures Exercise | Send Event Notification to PHEP Liaison 30 days in advance of exercise.
|  | Conduct or Participate in Exercise | Date TBD by OHA
Complete AAR within 60 days of exercise
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
| FY24 EXERCISE #2: (Title or brief description, including primary partnerships) | Send Event Notification to PHEP Liaison 30 days in advance of exercise.
Conduct or Participate in Exercise
Complete AAR within 60 days of exercise
Add identified improvement items to workplan or update plans within 60 days of exercise completion.
1,2 | QUARTERLY DRILL: LPHA will maintain 24/7/365 telephone availability for physicians, hospitals, other health care providers, OHA and the public to report public health emergencies within the LPHA service area. | DRILL: LPHA will successfully respond within 60 minutes to 24/7 after-hours emergency notification drills initiated by OHA and will take any corrective action needed within 30 days of notification. | Q1
Q2
Q3
Q4
1,2 | QUARTERLY DRILL: LPHA will maintain ability to receive emergency alerts from OHA. | DRILL: Within 60 minutes designated staff will confirm HAN alert testing. Designated staff include Health Officer, Communicable Disease (CD) Coordinator(s), Preparedness Coordinator, PIO, and LPHA County HAN Administrator. | Q1: 08/20/20
Q2: 09/10/2020
Q3: TBD
Q4: TBD
|  | Using results of quarterly HAN tests, review LPHA HAN to ensure users are updated, assigned their appropriate roles and that appropriate users are deactivated. |  | Mid Year: Year End:
1 | ANNUAL DRILL: LPHA will maintain ability to notify staff in the event of an emergency. | Initiate at least one local call down exercise/ drill for LPHA staff annually. |  |  |  | If the statewide HAN platform is not used for this process, LPHA must demonstrate through written procedures how public health staff and responding partners are notified during emergencies.
1-3 | LPHA will increase its capacity to serve persons with access and functional needs. | Exercises include considerations for persons with access and functional needs. (Describe)
Unplanned Drills and Exercises
Goal # | What Objective(s) Did This Unplanned Drill or Exercise Meet? | Name of Drill or Exercise |  | Date Completed | What staff or partners participated? | Additional Notes
ESF-8 INCIDENT AND RESPONSE ACTIVITIES
Activity |  |  |  | þ when Completed | Notes
LPHA participated in activities associated with local, regional, or statewide emerging threats or incidents as identified by HSPR or LPHA that includes timely assessment and sharing of essential elements of information for identification and investigation of an incident with public health impact, as agreed upon by HSPR and the CLHO Emergency Preparedness and Response subcommittee. |  |  |  | Completed N/A
CDC Cap. #s | Incident Name/OERS # |  | Date(s) | Activities and Outcomes |  | Date AAR Completed

## MYTEP Blank Template
XX County
updated xx/xx/2020
Purpose
The purpose of the Multi-year Training and Exercise Plan (MYTEP) is to provide training and exercise direction and goals in accomplishing the priorities. The activities outlined in this document are designed to build local capacity within the framework of the CDC Public Health Emergency Preparedness and Response Capabilities. The training and exercise schedule is a dynamic document updated and refined annually at minimum.
Training and Exercise Point(s) of Contact:
Name:
Title:
E-mail:
Phone:
Program Objectives Addressed:
1.
2.
3.
4.
5.
CDC PHEPR Capabilities Addressed:
1.
2.
3.
4.
5.
2021
January | February | March | April | May | June | July | August | September | October | November | December
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration
2022
January | February | March | April | May | June | July | August | September | October | November | December
Cascadia Rising
[7 empty] | HSPR ESF-8 Comms. Drill | HSPR ESF-8 Comms. Drill
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration
2023
January | February | March | April | May | June | July | August | September | October | November | December
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration
2024
Statewide Medical Countermeasures Exercise (Date TBD)
January | February | March | April | May | June | July | August | September | October | November | December
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration

## MYTEP Example
XX County
updated xx/xx/2020
Purpose
The purpose of the Multi-year Training and Exercise Plan (MYTEP) is to provide training and exercise direction and goals in accomplishing the priorities. The activities outlined in this document are designed to build local capacity within the framework of the CDC Public Health Emergency Preparedness and Response Capabilities. The training and exercise schedule is a dynamic document updated and refined annually at minimum.
Training and Exercise Point(s) of Contact:
Name: Amy Epi
Title: PHEP Coordinator/ Epidemiologist
E-mail: Amy.Epi@county.Health.org
Phone: 541-555-5555
Program Objectives Addressed:
1. LPHA will enhance its ability to support a surge event.
2. LPHA will increase its capacity to distribute medical countermeasures during an event requiring a coordinated response.
3. LPHA staff will increase their personal/family emergency preparedness plans.
4. LPHA will improve its cross-jurisdictional collaboration during a statewide or regional event.
5.
CDC PHEPR Capabilities Addressed:
1. Cap. 1: Community Preparedness
2. Cap 3: Emergency Operations Coordination
3. Cap 6: Information Sharing
4. Cap 8: Medical Countermeasures Dispensing and Administration
5. Cap. 10 Medical Surge
2020
January | February | March | April | May | June | July | August | September | October | November | December
[6 empty] | Annual facility generator startup drill |  | Preparedness Month Staff Training | Drive Thru Flu Shot Clinic | ICS 300 for LPHA staff and partners
[7 empty] | HSPR ESF-8 Comms. Drill | HSPR ESF-8 Comms. Drill
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration
2021
January | February | March | April | May | June | July | August | September | October | November | December
Alternate Care Facility TTX |  | Oregon Prepared Conference | OR-Epi Conference | Coalition Medical Surge FSE |  | Annual facility generator startup drill |  | Preparedness Month Staff Training
Annual Staff Notification Drill
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration
2022
January | February | March | April | May | June | July | August | September | October | November | December
| Local logistics TTX in preparation for Cascadia Rising | Oregon Prepared Conference | OR-Epi Conference | Coalition Medical Surge FSE | Cascadia Rising | Annual facility generator startup drill |  | Preparedness Month Staff Training |  | Closed POD Workshop with school district
Annual Staff Notification Drill
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration
2023
January | February | March | April | May | June | July | August | September | October | November | December
FY24: Statewide Medical Countermeasures Exercise (Date TBD)
Comms. FSE with Access and Functional Needs Partners |  | Oregon Prepared Conference | OR-Epi Conference | Coalition Medical Surge FSE |  | Annual facility generator startup drill |  | Preparedness Month Staff Training
|  | Annual Staff Notification Drill | [5 empty] | Closed POD FSE with school district
Capability 1: Community Preparedness | [5 empty] | Capability 9: Medical Materiel Management & Distribution
Capability 2: Community Recovery | [5 empty] | Capability 10: Medical Surge
Capability 3: Emergency Operations Coordination | [5 empty] | Capability 11: Nonpharmaceutical Interventions
Capability 4: Emergency Public Information and Warning | [5 empty] | Capability 12: Public Health Laboratory Testing
Capability 5: Fatality Management | [5 empty] | Capability 13: PH Surveillance & Epidemiological Investigation
Capability 6: Information Sharing | [5 empty] | Capability 14: Responder Safety and Health
Capability 7: Mass Care | [5 empty] | Capability 15: Volunteer Management
Capability 8: Medical Countermeasure Dispensing & Administration