**Timeline for public health modernization deliverables**

Conference of Local Health Officials

May 21, 2020

**Background:**

OHA postponed work on the 2020 public health accountability metrics report and the 2021-23 public health modernization funding formula. OHA plans to resume this work in the coming weeks so that these deliverables can be submitted by September to Legislative Fiscal Office through the 2020 Public Health Modernization Funding Report.

**Process and timeline:**

|  |  |
| --- | --- |
| **2020 Public Health Accountability Metrics Report** | |
| **PHAB Accountability Metrics subcommittee**   * Review 2020 data * Review report framing | Early June |
| **CLHO special webinar**   * Review 2020 data * Review report framing | Mid-June |
| **PHAB**   * Approve final 2020 report | June meeting, or next meeting |

|  |  |
| --- | --- |
| **2021-23 Public Health Modernization Funding Formula** | |
| **PHAB Incentives and Funding subcommittee**   * Finalize funding principles * Develop recommendations for public health modernization funding * Incorporate changes to funding formula based on feedback provided on funding formula implementation in 2019-21 | June-August |
| **CLHO meeting or special webinar**   * Review PHAB funding recommendations * Review changes to funding formula | August |
| **PHAB**   * Approve 2021-23 funding formula | August |