Title V Evidence-informed strategic measure (ESM) and State Performance Measure (SPM) Development Timeline (rev 7/8/15)

July 2015:

  - Block Grant will be submitted with new priority areas and plan for developing and launching strategies/ESMs and Developing the SPMs

  - State staff leads assigned to the new priority areas

  - Present timeline and request CLHO HF participation for Title V steering committee/co-leads

  - A&E contractor working to gather input on potential strategies/ESMs and SPMs from leads/national MCH experts, partners (survey) and best practice/lit review

August 2015:

  - State staff will be assigned to the new priority areas.

  - Title V Steering committee will be recruited and begin development of parameters for strategy development and implementation (including requirements, tracking/reporting structure, stakeholder engagement process, etc.)

  - State priority area leads/local co-leads will form work groups

Sept – Oct 2015:

  - Priority leads/teams will convene and begin work including development of briefs, engagement of stakeholder in development of potential strategies/ESMs, selection and implementation.

  - A&E staff and contractor will work with priority leads/co-leads to compile information on potential strategies/measures; survey LHDs, tribes, and partners on current and potential strategies/measures; develop materials on potential strategies/ESMs.

November/December 2015

  - Preliminary options for strategies/ESMs presented for input at priority-specific webinars mid-November.

  - All input synthesized and list of potential strategies/ESMs honed as needed.

January 2016

  - A&E contractor will deliver final report and materials for stakeholder meeting by Jan 8.

  - Priority leads/teams will present findings and recommendations on strategies/ESMs to LHDs and Tribes (day-long stakeholder meeting late Jan?)

  - Title V leadership will finalize menu of state and local level strategies/ESMs

  - Title V steering committee will finalize tracking and reporting guidelines for ESMs.

  - SPM Work group(s) convene(s) to develop SPMs and plan for SPM strategy development

February – March 2016:

  - LPHAs and Tribes will select which ESMs to work on and begin using their funds for the new priorities.

  - Local Title V strategy/ESM decisions will be reflected in March 1st MCH plan.

April 2016

  - State and Local Title V funding and work will align with Block Grant 3.0 priorities.

  - State and local NPM Strategy implementation begins

  - SPMS finalized.